## Title Page
Group Number: | ___________ | Sprint Number: | 2

## Backlog Estimating Example
Project Number | 6
Project Name: | UNCC Gaming Manager
Description: | Allows UNCC students who play video games to find and compete against other UNCC students looking to do the same. Host a tournament system where students cancompete against one another. Provide a platform that keeps track of Standings, Statistics, and User Preferences |  |  | PRODUCT BACKLOG
Team Members
Story # | Card Front | Card Back | Sprint Number | Priority | Assigned To | Comments | Estimated Size (Points) | Estimated Size (SML) | Estimated Size (Hours) | Estimated Velocity Per User Story
ST-0 | As a <user who wants this functionality> I need a <what the user wants> so that <why the user wants it>. | Acceptance Criteria <what the user should be able to do with the functionality> | [7 empty] | (Estimated Size / Estimated Hours)
ST - 1 | As a UNCC student, I need to be able to use my UNCC credentials so that I can use the website. | Logged into web site | Sprint 2 | 1st |  |  | 5 | S | 2 | 1
ST - 2 | As a UNCC student, I want to be able to search by platform, so that I can search for a match. | Searching on an entered search term categorized by Platform, returns results reflecting the search term(s) | Sprint 2 | 8th |  |  | 9 | M | 5 | 1
ST - 3 | As a UNCC student, I want to be able to search game titles, so that I can search for a match. | Searching on an entered search term categorized by Game Titles returns results reflecting the search term(s) | Sprint 2 | 9th |  |  | 9 | M | 5 | 1
ST - 4 | As a UNCC student, I want to be able to chat with the student I am matched with, so we can arrange the game. | Implement a working chat bar | Sprint 2 | 10th |  |  | 14 | L | 9 | 1
ST - 5 | As a Moderator and a UNCC student, I want the website to load quickly, so I don't waste time. | Less than 5 second load time between pages | Sprint 3 | 6th |  |  | 5 | S | 2 | 1
ST - 6 | As a Moderator, I want the site to also contain video game related news | Implement a News page | Sprint 3 | 11th |  |  | 5 | S | 2 | 1
ST - 7 | As a Moderator, I want our website database to be secure, so that the users passwords are safe. | Site encryption, SSO, is enabled. | Sprint 3 | 4rd |  |  | 5 | S | 2 | 1
ST - 8 | As a UNCC student I would like to implement a tournament system | Implement a tournament system for up to 1028 players. Requirements are modeled after "March Madness" tournament brackets. | Sprint 3 | 12th |  |  | 14 | L | 9 | 1
ST - 9 | As a UNCC student, I would like the layout to be clean, so that I can easily navigate it. | Web Standards and Usability Guidelines from https://webstandards.hhs.gov/guidelines/ are implemented accuractely. | Sprint 3 | 3rd |  |  | 5 | S | 2 | 1
ST - 10 | As a UNCC student, I would like to be able to create an account, so I can save my preferences. | Profile page implemented | Sprint 3 | 5th |  |  | 5 | S | 2 | 1
ST - 11 | As a Moderator, I would like the page to contain a list of popular games | Implement a table in the dataase to track them | Sprint 3 | 7th |  |  | 5 | S | 2 | 1
ST - 12 | As a Moderator, I first time users to see a first time tutorial after signing up | Tutorial splashscreen after user creation | Sprint 3 | 2nd |  |  | 9 | M | 5 | 1
[8 empty] | Total Estimated Hours/Velocity | 47 | 1
|  |  | Story Point Key | Estimated Hours
|  |  | Small | 2
|  |  | Medium | 5
|  |  | Large | 9

## Put your Answer Here
Project Number | 20
Project Name: | Yummi - POS Data Analytics
Description: | Software that can model data exports from common POS systems to allow managers/owners to effectively analyze sales, inventory, and staff data. |  |  | PRODUCT BACKLOG
Team Members | Sean DeHart, Rebekah Yermakovich, Sakshi Kaondal, Xan Jones, Elijah Robinson, Varun Pullakandam
Story # | Card Front | Card Back | Sprint Number | Priority | Assigned To | Comments | Estimated Size (SML) | Estimated Size (Hours) | Estimated Velocity Per User Story
ST-0 | As a <user who wants this functionality> I need a <what the user wants> so that <why the user wants it>. | Acceptance Criteria <what the user should be able to do with the functionality> | [6 empty] | (Estimated Size / Estimated Hours)
ST - 1 | As a manager/owner, I need to model sales over the course of the week, so that I can understand the restaurants output | Add a dashboard to display a graph of the data for that week | Sprint 2 | 1st | TDB |  | Large | 9
ST - 2 | As a manager/owner , I need to figure out why I am losing money while janice is working, so that I can find a way to increase sales | Show data for sales by employee clocked in | Sprint 3 | 13th | TDB |  | Small | 2
ST - 3 | As a manager, I need to view the stock of an item in inventory over time, so that inventory sales can be tracked | Add functions to visualize inventory over time | Sprint 3 | 14th | TDB |  | Small | 2
ST - 4 | As a manager/owner, I need to compare sales of multiple different products, so that I can track product sales | Add an option to specify items for the dashboard | Sprint 2 | 3rd | TDB |  | Medium | 5
ST - 5 | As a user, I need to visualize raw data that has been imported, so that I can verify the import is correct | Add a screen to show raw data after import | Sprint 2 | 4th | TDB |  | Large | 9
ST - 6 | As a restaurant owner, I want to use visualizations, so that I can improve restaurant sales | Create visualizations with the imported data | Sprint 2 | 5th | TDB | 5&6 would go hand and hand together | Medium | 5
ST - 7 | As a manager/owner, I need to receive hints on how I can use the information from my data, so that I am effeciently using the app | Show the user hints about their restaurant data(i.e. Item A sales are down 20% from last week) | Sprint 3 | 8th | TDB |  | Medium | 5
ST - 8 | As a user, I need to be able to login to an account, so that I can save my data so that I can track my performance | Add login capability | Sprint 2 | 2nd | TDB |  | Small | 2
ST - 9 | As a user, I need to scroll between different dashboards, so that I can quickly see various data visualizations | Add multiple dashboard displays and ability to change views | Sprint 3 | 7th | TDB |  | Medium | 5
ST - 10 | As a user, I need to customize dashboards by time period, so that I can track sales based on a certain time | Add a dashboard that can show sales based on a given time period | Sprint 2 | 6th | TDB |  | Small | 2
ST - 11 | As a user, I need to easily see predictions for upcoming days/week, so that I can make changes to increase sales | implement a predictive view for future sales | Sprint 3 | 15th | TDB |  | Large | 9
ST - 12 | As a user, I need to simulate effects of changing inventory rates, so that we can apply rates that increase sales | Implement view of updated inventory rates | Sprint 3 | 16th | TDB |  | Large | 9
ST - 13 | As a user who works at night, I need to have the option to enable dark mode/light mode, so that I can reduce eye strain | Implement a light/dark mode option to switch layout | Sprint 3 | 12th | TDB | 13&14 are very similar so if one is completed the other will be easy/small | Small | 2
ST - 14 | As a user, I need to categorize different products (ie. dessert, entrée, appetizer), so that I can view groups of data by category | Ability to show a variety of products and categorize them | Sprint 3 | 9th | TDB |  | Small | 2
ST - 15 | As a manager, I need to see when my staff is most productive, so that can schedule accordingly. | Show a visualization based upon selected staff | Sprint 3 | 11th | TDB | 15&16 are very similar so if one is completed the other will be easy/small | Medium | 5
ST - 16 | As a manager, I need to filter data based on operating staff, so that I can view scedules from previous days | Implement a data filter based on the name of the staff | Sprint 3 | 10th | TDB |  | Medium | 5
[7 empty] | Total Estimated Velocity | 78
|  |  | Story Point Key | Estimated Hours
|  |  | Small | 2
|  |  | Medium | 5
|  |  | Large | 9

## Done (hidden)
Project Number | 6
Project Name: | UNCC Gaming Manager | [7 empty] | Story Point Key (Sprint 2) | Estimated Hours | [6 empty] | Story Point Key (Sprint 3) | Estimated Hours
Description: | Allows UNCC students who play video games to find and compete against other UNCC students looking to do the same. Host a tournament system where students cancompete against one another. Provide a platform that keeps track of Standings, Statistics, and User Preferences | [7 empty] | Small | 3 | [6 empty] | Small | 6
Team Members | [8 empty] | Medium | 5 | [6 empty] | Medium | 10
[9 empty] | Large | 9 | [6 empty] | Large | 12
Note; This is an example of a "Done" page for Sprint 2 and Sprint 3. Replace your projects estimates and actuals | [6 empty] | Sprint 2 |  |  |  |  | Spriint 3
Story # | Card Front | Card Back | Sprint Number | Priority* | Total Estimated Size (S,M,L) | Total Estimated Size (Points) | Estimated Size (Hours) | Actual Hours | Estimated Velocity Delta | Actual Velocity Delta by Story |  | Total Estimated Size SML | Estimated Size (Hours) | Actual Hours | Estimated Velocity Delta | Actual Velocity Delta by Story | Assigned To | Comments
ST-0 | As a <user who wants this functionality> I need a <what the user wants> so that <why the user wants it>. | Acceptance Criteria <what the user should be able to do with the functionality> | [6 empty] | (Estimated Size / Estimated Hours) | (Estimated Hours / Actual Hours) |  |  |  |  | (Estimated Size / Estimated Hours) | (Estimated Points / Actual Hours)
ST - 1 | As a UNCC student, I need to be able to use my UNCC credentials so that I can use the website. | Logged into web site | Sprint 2 | 1st | S | 5 | 3 | 4 | 1 | 1.3333 | [6 empty] | Jane
ST - 2 | As a UNCC student, I want to be able to search by platform, so that I can search for a match. | Searching on an entered search term categorized by Platform, returns results reflecting the search term(s) | Sprint 2 | 8th | S | 5 | 3 | 7 | 1 | 2.3333 | [6 empty] | Joe
ST - 3 | As a UNCC student, I want to be able to search game titles, so that I can search for a match. | Searching on an entered search term categorized by Game Titles returns results reflecting the search term(s) | Sprint 2 | 9th | M | 9 | 5 | 9 | 1 | 1.8 | [6 empty] | Julie
ST - 4 | As a UNCC student, I want to be able to chat with the student I am matched with, so we can arrange the game. | Implement a working chat bar | Sprint 2 | 10th | M | 5 | 5 | 11 | 1 | 2.2 | [6 empty] | Joe
ST - 5 | As a Moderator and a UNCC student, I want the website to load quickly, so I don't waste time. | Less than 5 second load time between pages | Sprint 2 | 11th | L |  | 9 | 12 | 1 | 1.3333 | [6 empty] | Jane
ST - 6 | As a Moderator, I want the site to also contain video game related news | Implement a News page | Sprint 3 | 12th |  |  |  |  | 1 |  |  | M | 10 | 9 | 1 | 0.9 | Joe | This was moved from Sprint 1 to Sprint 2
ST - 7 | As a Moderator, I want our website database to be secure, so that the users passwords are safe. | Site encryption, SSO, is enabled. | Sprint 3 | 13th |  |  |  |  | 1 |  |  | L | 12 | 13 | 1 | 1.0833 | Jane
ST - 8 | As a UNCC student I would like to implement a tournament system | Implement a tournament system for up to 1028 players. Requirements are modeled after "March Madness" tournament brackets. | Sprint 3 | 14th |  |  |  |  | 1 |  |  | S | 6 | 7 | 1 | 1.1667 | Joe
ST - 9 | As a UNCC student, I would like the layout to be clean, so that I can easily navigate it. | Web Standards and Usability Guidelines from https://webstandards.hhs.gov/guidelines/ are implemented accuractely. | Sprint 3 | 15th |  |  |  |  | 1 |  |  | L | 12 | 13 | 1 | 1.0833 | Julie
ST - 10 | As a UNCC student, I would like to be able to create an account, so I can save my preferences. | Profile page implemented | Sprint 3 | 16th |  |  |  |  | 1 |  |  | S | 6 | 5 | 1 | 0.83333 | Julie
|  |  |  | Sprint 2 |  | Velocity per Sprint | 16 | 43 |  |  | Sprint 3 |  | 46 | 47
* It might not conform to the Sprint numbers here, but remains same as your group decided in the initial sprint | [5 empty] | Velocity per Sprint Delta | Velocity per Sprint | 43 |  |  |  |  | Velocity per Sprint | 47
[7 empty] | Velocity per Sprint Delta | 2.6875 |  |  |  |  | Velocity per Sprint Delta | 1.0217

## Doing (hidden)
[12 empty] | Story Point Key (Sprint 4) | Estimated Hours
Project Number | 6 | [10 empty] | Small | 6
Project Name: | UNCC Gaming Manager | [10 empty] | Medium | 10
Description: | Allows UNCC students who play video games to find and compete against other UNCC students looking to do the same. Host a tournament system where students cancompete against one another. Provide a platform that keeps track of Standings, Statistics, and User Preferences |  |  |  | DOING | [6 empty] | Large | 12
Team Members
Story # | Card Front | Card Back | Estimated Size | Estimated Size (Points) | Estimated Size (Hours) | Actual Hours | Estimated Velocity Delta | Actual Velocity | Sprint Number | Priority | Assigned To | Comments
ST-0 | As a <user who wants this functionality> I need a <what the user wants> so that <why the user wants it>. | [5 empty] | (Estimated Size / Estimated Hours) | (Estimated Points / Actual Hours)
ST - 11 | As a Moderator, I would like the page to contain a list of popular games | Implement a table in the dataase to track them | S | 3 | 6 |  | 1 | #DIV/0! | Sprint 4 | 17th | Jane
ST - 4
ST - 5
ST - 6
ST - 7
ST - 8
ST - 9
ST - 10
ST - 11
ST - 12

## To-do (hidden)
[9 empty] | Story Point Key (Sprint 4) | Estimated Hours
Project Number | 6 | [7 empty] | Small | 6
Project Name: | UNCC Gaming Manager | [7 empty] | Medium | 10
Description: | Allows UNCC students who play video games to find and compete against other UNCC students looking to do the same. Host a tournament system where students cancompete against one another. Provide a platform that keeps track of Standings, Statistics, and User Preferences |  |  | TO-DO |  |  |  |  | Large | 12
Team Members
Story # | Card Front | Card Back | Sprint Number | Priority | Assigned To | Comments | Estimated Size (Points) | Estimated Size (SML) | Estimated Size (Hours) | Estimated Velocity Delta
ST-0 | As a <user who wants this functionality> I need a <what the user wants> so that <why the user wants it>. | Acceptance Criteria <what the user should be able to do with the functionality> | [7 empty] | (Estimated Size / Estimated Hours)
ST - 12 | As a Moderator, Iwant first time users to see a first time tutorial after signing up | Tutorial splashscreen after user creation | Sprint 4 | 2nd | ? |  | 9 | L | 12 | 1

## Burndown Chart (hidden)
Sprint management template |  |  | Author: Rishikesh Parkhe
Number of days | 10
Starting Story points | 120
Ideal burn-rate | 13.3333 | Current Day SP | 112 | 8
Every day updates
Day | Ideal | Actual burnt | Velocity
1 | 120 | 120 | 0
2 | 106.6667 | 110 | 10
3 | 93.3333 | 102 | 8
4 | 80 | 100 | 2
5 | 66.6667 | 98 | 2
6 | 53.3333 | 88 | 10
7 | 40 |  | 88
8 | 26.6667 |  | 0
9 | 13.3333 |  | 0
10 | 0 |  | 0

## Story Point Velocity (hidden)
Story Point Velocity**
Story points per sprint
| Velocity | Sprint 2 | Sprint 3 | Sprint 4 | Totals
| Estimated | 16 | 47 | 45 | 108*
| Actual | 43 | 46
| Delta | 27 | -1
| Actual | 42 | 45
| Delta | 2.6875 | 1.0217
*Recalculated after Sprint 2. Since team is new to story points, as expected they experienced a significant miss in Sprint 1 Estimate
** Each Sprint needs to be of the same length for this to be a valid way to calculate velocity